## Holidays
2019-12-25 | Christmas Day
2019-12-30 | Rizal Day
2020-01-01 | New Year's Day
2020-01-25 | Chinese New Year
2020-02-25 | EDSA Revolution Anniversary
2020-04-09 | Maundy Thursday
2020-04-10 | Good Friday
2020-04-11 | Black Saturday
2020-05-01 | Labor Day
2020-05-24 | Eidul Fitr
2020-06-12 | Independence Day
2020-07-31 | Eidul Adha
2020-08-21 | Ninoy Aquino Day
2020-08-31 | National Heroes Day
2020-11-01 | All Saints' Day
2020-11-02 | All Souls' Day
2020-11-30 | Bonifacio Day
2020-12-08 | Immaculate Conception
2020-12-24 | Christmas Holiday
2020-12-25 | Christmas Day
2020-12-30 | Rizal Day
2020-12-31 | New Year's Eve

## Input
Course | Tasks | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status | Remarks
Getting Grounded on Analytics | SME Onboarding | 2019-11-25 | 2019-12-06 | 2019-11-25 | 2019-12-06 | Completed
Getting Grounded on Analytics | Documentary Requirements Completion | 2019-11-29 | 2019-12-19 | 2019-12-12 | 2019-12-19 | Completed
Getting Grounded on Analytics | Video Content Production Shoots | 2019-12-20 | 2020-01-07 | 2019-12-20 | 2020-01-20 | Completed
Getting Grounded on Analytics | Video Content Post-production | 2020-01-08 | 2020-01-31 | 2019-12-23 | 2020-01-24 | Completed
Getting Grounded on Analytics | Beta Testing | 2020-02-03 | 2020-02-14 | 2020-01-20 | 2020-01-24 | Completed
Getting Grounded on Analytics | Launch | 2020-02-17 | 2020-02-19 | 2020-01-27 | 2020-01-27 | Completed
Essential Excel Skills for Business | SME Onboarding | 2019-11-19 | 2019-11-22 | 2019-12-29 | 2020-01-08 | Completed | Change of SME due to unplanned undercapacity
Essential Excel Skills for Business | Documentary Requirements Completion | 2019-11-29 | 2019-12-19 | 2020-01-08 | 2020-01-14 | Completed | Change of SME due to unplanned undercapacity
Essential Excel Skills for Business | Video Content Production Shoots | 2020-01-06 | 2020-01-17 | 2020-01-20 | 2020-01-24 | Completed | Reschedule due to effects of Taal eruption
Essential Excel Skills for Business | Video Content Post-production | 2020-01-20 | 2020-02-12 | 2020-02-04 |  | Completed
Essential Excel Skills for Business | Beta Testing | 2020-02-13 | 2020-02-27 | 2020-02-10 |  | Completed
Essential Excel Skills for Business | Launch | 2020-02-28 | 2020-03-03 |  |  | Completed
SQL for Business Users | SME Onboarding | 2020-03-26 | 2020-03-30 | 2020-03-30 |  | Completed
SQL for Business Users | Documentary Requirements Completion | 2020-03-31 | 2020-04-30 | 2020-04-30 |  | In-progress
SQL for Business Users | Video Content Production Shoots | 2020-04-04 | 2020-04-20 | 2020-05-04 |  | Not Started
SQL for Business Users | Video Content Post-production | 2020-04-21 | 2020-05-15 |  |  | Not Started
SQL for Business Users | Beta Testing | 2020-05-18 | 2020-05-29 |  |  | Not Started
SQL for Business Users | Launch | 2020-06-01 | 2020-06-03 |  |  | Not Started
Computing in Python | SME Onboarding |  |  |  |  | In-progress
Computing in Python | Documentary Requirements Completion |  |  |  |  | Not Started
Computing in Python | Video Content Production Shoots |  |  |  |  | Not Started
Computing in Python | Video Content Post-production |  |  |  |  | Not Started
Computing in Python | Beta Testing |  |  |  |  | Not Started
Computing in Python | Launch |  |  |  |  | Not Started
Data Visualization Fundamentals | SME Onboarding | 2019-12-29 | 2020-01-08 | 2020-02-01 |  | Completed
Data Visualization Fundamentals | Documentary Requirements Completion | 2020-01-27 | 2020-02-14 | 2020-04-30 |  | In-progress
Data Visualization Fundamentals | Video Content Production Shoots | 2020-02-18 | 2020-03-03 | 2020-05-04 |  | Not Started
Data Visualization Fundamentals | Video Content Post-production | 2020-03-04 | 2020-03-27 |  |  | Not Started
Data Visualization Fundamentals | Beta Testing | 2020-03-30 | 2020-04-14 |  |  | Not Started
Data Visualization Fundamentals | Launch | 2020-04-15 | 2020-04-17 |  |  | Not Started
SQL for Data Engineering | SME Onboarding |  |  |  |  | Completed
SQL for Data Engineering | Documentary Requirements Completion |  |  |  |  | In-progress
SQL for Data Engineering | Video Content Production Shoots |  |  |  |  | Not Started
SQL for Data Engineering | Video Content Post-production |  |  |  |  | Not Started
SQL for Data Engineering | Beta Testing |  |  |  |  | Not Started
SQL for Data Engineering | Launch |  |  |  |  | Not Started
Statistical Analysis and Modeling using Excel | SME Onboarding | 2019-11-19 | 2019-11-22 | 2019-11-19 | 2019-11-22 | Completed
Statistical Analysis and Modeling using Excel | Documentary Requirements Completion | 2019-11-29 | 2019-12-19 | 2020-01-15 | 2020-01-27 | In-progress | SME undercapacitized. No alternate SME for the course.
Statistical Analysis and Modeling using Excel | Video Content Production Shoots | 2020-01-20 | 2020-01-31 | 2020-01-29 |  | In-progress | Rescheduled 3x. Reasons were: (1) Due to Taal eruption, (2) SME undecapacity, and (3) output freeze until AAP project resources' LOI sign-off and payment
Statistical Analysis and Modeling using Excel | Video Content Post-production | 2020-02-03 | 2020-02-27 |  |  | Not Started
Statistical Analysis and Modeling using Excel | Beta Testing | 2020-02-28 | 2020-03-12 |  |  | Not Started
Statistical Analysis and Modeling using Excel | Launch | 2020-03-13 | 2020-03-17 |  |  | Not Started
Data-driven Research Fundamentals | SME Onboarding | 2019-12-16 | 2019-12-23
Data-driven Research Fundamentals | Documentary Requirements Completion | 2020-02-03 | 2020-02-21
Data-driven Research Fundamentals | Video Content Production Shoots | 2020-02-24 | 2020-03-09
Data-driven Research Fundamentals | Video Content Post-production | 2020-03-10 | 2020-04-02
Data-driven Research Fundamentals | Beta Testing | 2020-04-03 | 2020-04-20
Data-driven Research Fundamentals | Launch | 2020-04-21 | 2020-04-23
Data Management Fundamentals | SME Onboarding | 2019-12-17 | 2019-12-19 | 2019-12-17 | 2019-12-19 | Completed
Data Management Fundamentals | Documentary Requirements Completion | 2019-12-20 | 2020-01-03 | 2020-01-17 |  | In-progress | SME undercapacitized. No alternate SME for the course. Submission of presentation deck and exit assessments on hold due output freeze until AAP project resources' LOI sign-off and payment.
Data Management Fundamentals | Video Content Production Shoots | 2020-01-06 | 2020-01-17 | 2020-01-20 | 2020-01-20 | Completed
Data Management Fundamentals | Video Content Post-production | 2020-01-20 | 2020-02-12 |  |  | Not Started
Data Management Fundamentals | Beta Testing | 2020-02-13 | 2020-02-27 |  |  | Not Started
Data Management Fundamentals | Launch | 2020-02-28 | 2020-03-03 | 2020-05-15 |  | Not Started
Enterprise Data Governance | SME Onboarding | 2019-12-17 | 2019-12-19
Enterprise Data Governance | Documentary Requirements Completion | 2020-01-20 | 2020-02-07
Enterprise Data Governance | Video Content Production Shoots | 2020-02-10 | 2020-02-21
Enterprise Data Governance | Video Content Post-production | 2020-02-24 | 2020-03-19
Enterprise Data Governance | Beta Testing | 2020-03-20 | 2020-04-02
Enterprise Data Governance | Launch | 2020-04-03 | 2020-04-07
Storytelling using Data | SME Onboarding | 2019-12-29 | 2020-01-08
Storytelling using Data | Documentary Requirements Completion | 2020-03-04 | 2020-03-24
Storytelling using Data | Video Content Production Shoots | 2020-03-25 | 2020-04-07
Storytelling using Data | Video Content Post-production | 2020-04-08 | 2020-05-06
Storytelling using Data | Beta Testing | 2020-05-07 | 2020-05-20
Storytelling using Data | Launch | 2020-05-21 | 2020-05-25
Data Visualization using Python and Tableau | SME Onboarding | 2019-12-03 | 2019-12-06 | 2019-12-03 | 2019-12-06 | Completed
Data Visualization using Python and Tableau | Documentary Requirements Completion | 2020-02-03 | 2020-02-21 | 2020-02-04 |  | In-progress
Data Visualization using Python and Tableau | Video Content Production Shoots | 2020-02-24 | 2020-03-09 |  |  | Not Started
Data Visualization using Python and Tableau | Video Content Post-production | 2020-03-10 | 2020-04-02 |  |  | Not Started
Data Visualization using Python and Tableau | Beta Testing | 2020-04-03 | 2020-04-20 |  |  | Not Started
Data Visualization using Python and Tableau | Launch | 2020-04-21 | 2020-04-23 |  |  | Not Started
Experimental Design and Analysis | SME Onboarding | 2019-11-19 | 2019-11-22
Experimental Design and Analysis | Documentary Requirements Completion | 2020-03-10 | 2020-03-30
Experimental Design and Analysis | Video Content Production Shoots | 2020-03-31 | 2020-04-15
Experimental Design and Analysis | Video Content Post-production | 2020-04-16 | 2020-05-12
Experimental Design and Analysis | Beta Testing | 2020-05-13 | 2020-05-26
Experimental Design and Analysis | Launch | 2020-05-27 | 2020-05-29
Python for Data Engineering | SME Onboarding | 2020-01-07 | 2020-01-13 | 2020-01-07 | 2020-01-13 | Completed
Python for Data Engineering | Documentary Requirements Completion | 2020-01-14 | 2020-02-05 |  |  | In-progress
Python for Data Engineering | Video Content Production Shoots | 2020-02-10 | 2020-02-14 |  |  | Not Started | Reschedule due to output freeze unti AAP Project Resources' LOI sign-off and payment
Python for Data Engineering | Video Content Post-production | 2020-02-17 | 2020-03-12 |  |  | Not Started
Python for Data Engineering | Beta Testing | 2020-03-13 | 2020-03-26 |  |  | Not Started
Python for Data Engineering | Launch | 2020-03-27 | 2020-03-31 |  |  | Not Started
Advanced Data Engineering | SME Onboarding | 2020-01-07 | 2020-01-13
Advanced Data Engineering | Documentary Requirements Completion | 2020-02-05 | 2020-02-26
Advanced Data Engineering | Video Content Production Shoots | 2020-02-27 | 2020-03-11
Advanced Data Engineering | Video Content Post-production | 2020-03-12 | 2020-04-06
Advanced Data Engineering | Beta Testing | 2020-04-07 | 2020-04-22
Advanced Data Engineering | Launch | 2020-04-23 | 2020-04-27
Statistical Analysis and Modeling using SQL and Python | SME Onboarding | 2020-01-07 | 2020-01-13
Statistical Analysis and Modeling using SQL and Python | Documentary Requirements Completion | 2020-03-12 | 2020-04-01
Statistical Analysis and Modeling using SQL and Python | Video Content Production Shoots | 2020-04-02 | 2020-04-17
Statistical Analysis and Modeling using SQL and Python | Video Content Post-production | 2020-04-20 | 2020-05-14
Statistical Analysis and Modeling using SQL and Python | Beta Testing | 2020-05-15 | 2020-05-28
Statistical Analysis and Modeling using SQL and Python | Launch | 2020-05-29 | 2020-06-02
Data Science and Machine Learning using Python | SME Onboarding | 2019-12-04 | 2019-12-06
Data Science and Machine Learning using Python | Documentary Requirements Completion | 2020-03-02 | 2020-03-20
Data Science and Machine Learning using Python | Video Content Production Shoots | 2020-03-24 | 2020-04-06
Data Science and Machine Learning using Python | Video Content Post-production | 2020-04-07 | 2020-05-05
Data Science and Machine Learning using Python | Beta Testing | 2020-05-06 | 2020-05-19
Data Science and Machine Learning using Python | Launch | 2020-05-20 | 2020-05-22
Deep Learning using Python | SME Onboarding | 2019-12-04 | 2019-12-06
Deep Learning using Python | Documentary Requirements Completion | 2020-04-16 | 2020-05-07
Deep Learning using Python | Video Content Production Shoots | 2020-05-08 | 2020-05-21
Deep Learning using Python | Video Content Post-production | 2020-05-22 | 2020-06-17
Deep Learning using Python | Beta Testing | 2020-06-30 | 2020-07-13
Deep Learning using Python | Launch | 2020-07-14 | 2020-07-16
Improving Employee and Customer Experience using Analytics | SME Onboarding | 2019-11-25 | 2019-12-06 | 2019-11-25 | 2019-12-06 | Completed
Improving Employee and Customer Experience using Analytics | Documentary Requirements Completion | 2020-05-04 | 2020-05-22 |  |  | Not Started
Improving Employee and Customer Experience using Analytics | Video Content Production Shoots | 2020-05-25 | 2020-06-05 |  |  | Not Started
Improving Employee and Customer Experience using Analytics | Video Content Post-production | 2020-06-08 | 2020-07-02 |  |  | Not Started
Improving Employee and Customer Experience using Analytics | Beta Testing | 2020-07-03 | 2020-07-16 |  |  | Not Started
Improving Employee and Customer Experience using Analytics | Launch | 2020-07-17 | 2020-07-21 |  |  | Not Started
Data Science and Analytics Project Management | SME Onboarding | 2019-11-25 | 2019-12-05 | 2019-11-25 | 2019-12-05 | Completed
Data Science and Analytics Project Management | Documentary Requirements Completion | 2020-04-01 | 2020-04-23 |  |  | Not Started
Data Science and Analytics Project Management | Video Content Production Shoots | 2020-04-24 | 2020-05-08 |  |  | Not Started
Data Science and Analytics Project Management | Video Content Post-production | 2020-05-11 | 2020-06-03 |  |  | Not Started
Data Science and Analytics Project Management | Beta Testing | 2020-06-04 | 2020-06-18 |  |  | Not Started
Data Science and Analytics Project Management | Launch | 2020-06-19 | 2020-06-23 |  |  | Not Started
Analytics Applications in Finance and Risk | SME Onboarding | 2019-11-27 | 2019-12-11 | 2019-11-27 | 2019-12-11 | Completed
Analytics Applications in Finance and Risk | Documentary Requirements Completion | 2020-06-01 | 2020-06-22 |  |  | Not Started
Analytics Applications in Finance and Risk | Video Content Production Shoots | 2020-06-23 | 2020-07-06 |  |  | Not Started
Analytics Applications in Finance and Risk | Video Content Post-production | 2020-07-07 | 2020-07-30 |  |  | Not Started
Analytics Applications in Finance and Risk | Beta Testing | 2020-08-03 | 2020-08-14 |  |  | Not Started
Analytics Applications in Finance and Risk | Launch | 2020-08-17 | 2020-08-19 |  |  | Not Started
Formulas:
Target End Date = WORKDAY([Target Start Date],14,Holidays!$A1:A22)
Target Start Date = WORKDAY([Target End Date, row above],1,Holidays!$A1:A22)
Target Start Date = WORKDAY([Target End Date],-2,Holidays!$A1:A22)
Actual Start Date = WORKDAY([Actual Start Date, row above],1,Holidays!$A1:A22)

## SME assignments
Course Name | SME | % | Content Materials | Endorsement/VShoot | CV | LOI | COR | Sign-Off
Getting Grounden on Analytics | Sherwin Pelayo | 100% | [6 empty] | Legend
Designing and Building Data Products
Essential Excel Skills for Data Preparation and Analysis | Gabriel Kristopher Soong | 100%
Computing in Python | Dominic Vincent Ligot | 100%
SQL for Business Users | Dominic Vincent Ligot | 100%
Data Management Fundamentals | Dominic Vincent Ligot | 100%
Enterprise Data Governance | Dominic Vincent Ligot | 100%
Dashboards and Drill-down Analytics | Frances Claire S. Tayco | 100%
Data Visualization Fundamentals | Gabriel Kristopher Soong | 100%
Data Visualization using Python and Tableau | Ruben D. Canlas, Jr. | 100%
Storytelling using Data
Data-driven Research Fundamentals | Eugene Rex L. Jalao, Ph.D. | 100%
Experimental Design and Analysis
SQL for Data Engineering | Richard D. Vinas
Python for Data Engineering | Pierre Allan Villena | 50%
| Simon Anthony Lorenzo | 50%
Advanced Data Engineering | Raymond Freth A. Lagria | 95%
| Pierre Allan Villena | 2.5%
| Simon Anthony Lorenzo | 2.5%
Statistical Analysis and Modeling using Excel | Frances Claire S. Tayco | 100%
Statistical Analysis and Modeling using SQL and Python | Raymond Freth A. Lagria | 50%
| Carlo Angelo A. Sonday | 50%
Data Science and Machine Learning using Python | Carlos Alexander N. Almendral | 100%
Deep Learning using Python | Carlos Alexander N. Almendral | 100%
Improving Customer and Employee Experience using Analytics | Sherwin Pelayo | 100%
Analytics Applications in Operations
Analytics Applications in Finance and Risk | Macrina P. Lazo | 100%
Data Science and Analytics Project Management | Michelle Alarcon | 100%